## Event Planning Basics
Event Planning
Where Do I Start?
Form a committee (you cannot do this alone)
Volunteers should be used for as many positions as possible!
Use Chapterpedia for ideas
Go through planning worksheet
BE FLEXIBLE
Create a Budget
Follow/Create Timeline
Evaluate Your Events
Celebrate Volunteers

## Event Planning Timeline
Suggested Event Planning Timeline
4-6 months out
Determine committees & each committee’s assignments. Committees for consideration include: venue & logistics, volunteers, sponsorships, ticket sales, hospitality, promotion/social media/PR.
Determine the size and scope of your event.
Determine event date
Establish planning meeting frequency and time, schedule remaining planning meetings
Develop event goals, objectives, program outline, and key communication messages for advertising
Find a venue and confirm reservation
Identify keynote speakers and/or conductor
Prepare budget estimate
Discuss invitation list (including those who should receive personal invitation)
Design and develop event database for mailing invitations and tracking RSVPs
Initiate design process for invitation and program
Discuss A/V needs
3-4 months out
Create or prep event promo videos, social media shares, invitations, sponsor letters, etc
Develop draft program
Develop publicity pieces
Create buzz on blogs and member forums
Create a webpage, Eventbrite, Facebook event, etc. (Be sure to include check box on sign up page allowing for photography).
Begin sharing “save the date” or “get ready for the student send-off” on social media.
Gather speaker bios and pictures if needed
Select caterer, establish menu, and confirm date on their calendar.
Plan any room decorations, tables, chairs, linens, etc.
Reserve photographer/videographer
Sponsor levels/amounts
Investigate need for special permits, licenses, insurance, etc
Order thank you gifts
Check and order necessary supplies (name badges, pens, envelopes, notebook, wrapping paper
Confirm speaker including av needs and transportation/lodging
2 months out
Determine what special services (audio visual, sound system) are needed & reserve, and relay information to venue
Create a volunteer sign up genius or other way to get needed volunteers
Email invite to alumni office for mass distribution
Press release
Prepare a Contingency Plan
Follow up with sponsors
1 week ahead
Prepare conducting notes, including assignment of prayers, introductions, instructions, sponsor thank yous and “housekeeping” items
Have all committeee member meet and confirm all details against master plan and ensure back-up plans are developed for any situation
Determine if any directional signage is needed at the facility
Finalize script
Brief any hosts, greeters, volunteers about their event duties and timelines
Provide final number to caterer
Record RSVPs
Print program
Send agenda
List photo opportunities
Confirm catering
Confirm av
Confirm set up
Run final name badges
Make confirmation phone calls
Venue walk through
1 day ahead
Send final email reminder to invitees.
Have checks cut for vendors, as needed.
Ensure all signage is in place
Ensure registration table is stocked with necessary items (name badges, registration sheet, paper, pens, tape)
Ensure all items are ready to go (t-shirt, swag, paper products)
Check weather report
Day of event
Arrive at location early for set-up
Bring registration materials: guest lists, name badges, etc.
Check-in with each committee person to make sure they're ready and answer questions
Check room to make sure it is clean and holds the necessary equipment and furniture.
Meet caterer or setup food.
Set up signage.
Meet DJ, photographer, etc.
Check wifi, sound system test, etc.
Place water at the podium if having a speaker.
Setup registration table/name tags and/or distribute programs. Have a Master list of all attendees.
If recording event, collect media services release forms from speakers and give to media services staff.
Photograph & collect stories/quotes.
Have someone social share during the event.
Reserve seating for VIP/guests. Assign someone to be their escort.
Post event
Distribute thank you gift--sponsors, volunteers, speakers, donors, media
Pay vendors
Distribute photos
Hold event debrief meeting
Update database
File materials to help with future events
Financial status: gather all receipts, documentation, final registration data
Post event publicity--post on Facebook
Survey attendees for feedback.
Send a summary of your event (with photos) to Alumni Relations!
Follow up communication

## Event Budget
EVENT BUDGET
Items | Estimated Cost | Actual Cost | Who Pays | Deposit Full Payment (date) | Confirmation#
Site cost
Room Rental
Parking Charges
Security Charges
Catering and Meal Services
Beverages
Food
Paper producets
Service Charges
Delivery
Gratuity
Rentals and/or decoration services
Tables and Chairs
Decorations
Inflatables
Entertainment Costs
Speaker Fee
Speaker per diem and lodging
Advertising
Facebook ad
Flyers
Print
Other
Insurance
Hosting gifts
Photographer
Supplies
Funding Sources

## Worksheet
Event Planning Worksheet
PRIMARY EVENT INFORMATION
Chairperson |  | Contact Information
Activity |  | Event Date
Event Location |  | Event Start Time
Numbers Anticipated |  | Event End Time
Objectives
COMMITTEE MEMBERS
Name |  | Contact Information
Name |  | Contact Information
Name |  | Contact Information
Name |  | Contact Information
Name |  | Contact Information
Name |  | Contact Information
PROGRAM EXPENSES
Facility |  | Signs
Flyers |  | Postage
Nametags |  | Other
Refreshments |  | Other
Handouts
PUBLICITY
Flyers | Date: | Date:
News/PR | Deadline:
Website updated | Date: | Date:
Signs/Banners Requested | Date:
Social Media | Date: | Date:
EventBrite/Emails | Date:
EQUIPMENT & AUDIOVISUAL NEEDS
Item: | Location: | Quantity:
Item: | Location: | Quantity:
Item: | Location: | Quantity:
Item: | Location: | Quantity:
Item: | Location: | Quantity:
FUNDING AND FINANCE
Prepare Detail Budget
Identify appropriate funding sources (sponsorships, admission costs, etc.)
Checklist
OK with insurance |  | Catering requested
Volunteers confirmed |  | Print registration list
Parking logistics |  | Print Name tag
Signage |  | Room set-up
Decorations |  | Registration Table
Thank you gifts
Music
Photography
Develop Program
Invitation created

## Special Event Instructions
Special Instructions for Formal Dinner event planning:
6 months prior | Contact speakers/performers/participants to determine availability.
6 months prior | Determine ticket prices, distribution and policies, including special discounts for families or large groups. (Are we going to sell tickets? How will the selling happen? Who is to negotiate with the ticket office?)
4-5 months prior | Contact pianist for music during event.
2-3 months prior | Finalize catering arrangements.
2-3 months prior | Create a volunteer sign up genius or other way to get needed volunteers.
To schedule a Performing Arts Event:
6 Months prior to event | fill out the Performance Site Questionnaire on https://pam.byu.edu/wp-content/uploads/2015/06/PSQ-English-Fillable-2.pdf
6 months prior to event | determine if your venue requires a certificate of insurance. Available at https://pam.byu.edu/wp-content/uploads/2016/02/Certificates-of-Insurance-Coverage-Info.pdf
5 months prior to event | print event tickets
For any other questions go to https://pam.byu.edu/
Special Instructions for planning a 5K:
6 months prior to events | Secure event permit for our race location from the school district, city, police or whoever is needed for the event.
6 months prior to event | Request a certificate of insurance through Roy at roy.brinkerhoff@byu.edu
3. 6 Months prior to event | Hire a timing company if you want the race professionally timed.
4-5 months prior to event | Contact potential donors (i.e. silent auction donations, ect)
5. 2-3 months prior to event | Line up a t-shirt vendor, don’t order until 2-3 weeks out.
2-3 months prior to event | Order medals for to two finishers in each age category.
2-3 months prior to event | Arrange for medical services and personal. Arrange for waivers to be signed.
2 weeks prior to event | Order a generator for the DJ; may need to coordinate this depending on the location of the race.
2 weeks prior to event | Arrange for Port-a-Potties at the race site. This is easy to arrange through local companies.
2 weeks prior to event | Create a race map of the trail.
Special Instructions to email new/current students for Student Send-off event:
Log into Alumni3.byu.edu
Under the Student Section there is three options; New Students lists, Current Students List, Email to Students from Chapter. Click on Email to Students from Chapter
On the next screen, click on “Submit a new mailing for approval”
On the next screen, ensure that you have chosen to send your email to the right student audience, whether current or new students. Fill in the email approval form and click submit for approval
Request student swag (pencils, etc.) from BYU Alumni Staff
Special Instructions for Golf Tournament planning:
6 months prior to the event | Determine ticket prices, distribution and policies, including special discounts for families or large groups.
6 months prior to the event | Determine how sponsors will be recognized (need established before you can invite).
4-5 months prior to the event | Begin contacting potential sponsors (i.e. silent auction donations, ect)
Special Instructions for Speakers Bureau event planning:
6 months prior to the event | Use speakers bureau, http://alumni3.byu.edu/speakersbureau/ , to request a speaker.
4-5 months prior to the event | Book travel arrangements and communicate travel reimbursement guidelines to participants.
2-3 months prior to event | Reach out to speakers and create travel plan.
2 weeks prior to event | Finalize travel logistics with Speaker.
Special Instructions for Tailgate event planning:
6 months prior to the event | Contact speakers/performers/participants to determine availability.
6 months prior to the event | Determine ticket prices, distribution and policies, including special discounts for families or large groups. (Are we going to sell tickets? How will the selling happen? Who is to negotiate with the ticket office?)